## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project (AI-Powered Customer Support Quality Auditor) | MUST HAVE | No Dependency | Shivamani | 3- Completed
S1 | S1 | US-001 | Milestones Discussed and SRS Planned | SHOULD HAVE | No Dependency | Shivamani | 3- Completed
S1 | S1 | US-001 | Tech Stack Finalized and GIT initialization and repository setup | MUST HAVE | GIT | Shivamani | 3- Completed
S2 | S2 | US-002 | Project Initialization and Concepts and Brainstroming | COULD HAVE | No Dependency | Shivamani | 3- Completed
S2 | S2 | US-002 | Libraries and Workflow and Basic Whisper Setup | MUST HAVE | WebRTC,Python and Whisper STT | Shivamani | 3- Completed
S3 | S3 | US-003 | Concepts of Different types Embedding and Tranformers | SHOULD HAVE | WORD2VEC and OpenAI | Shivamani | 3- Completed
S3 | S3 | US-003 | Natural Language Processing and AI API's | SHOULD HAVE | Gemini AI Studio | Shivamani | 3- Completed
S4 | S4 | US-004 | RAG Concepts & RAG Inplementation Overview | SHOULD HAVE | LangChain | Shivamani | 3- Completed
S5 | S5 | US-005 | Make Application Orchestrator & Audio Processor | MUST HAVE | python,Streamlit and Senko/WebRTC | Shivamani | 3- Completed
S5 | S5 | US-005 | Chat Normalizer & DB Manager and RAG engine | MUST HAVE | Python,JSON and Sqlite/Langchain | Shivamani | 3- Completed
S5 | S5 | US-005 | Auditor & Reporting | MUST HAVE | Google Gen AI and SMTPLIB & FPDF | Shivamani | 3- Completed
S6 | S6 | US-006 | Bugs Error fixing code upts policy update personal reporting code | MUST HAVE | No Dependency | Shivamani | 3- Completed
S6 | S6 | US-006 | Handling env variables and policy fiies | MUST HAVE | DOT-ENV | Shivamani | 3- Completed
S7 | S7 | US-007 | Theory and Implementation of Docker & DOCKER CONFIGURATION | SHOULD HAVE | Docker | Shivamani | 3- Completed
S7 | S7 | US-007 | DOCKER IMAGE AND CONTAINER | SHOULD HAVE | Docker | Shivamani | 3- Completed
S8 | S8 | US-008 | Documentation and Implementation | SHOULD HAVE | GITHUB | Shivamani | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 52.5 | 13 | 15 | 11.5 | 7.5 | 3 | 1.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to project( GenAI-Powered Customer Support Quality Auditor. ) | 2025-12-07 | 2025-12-08 | Shivamani | others | 3-completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Milestones Discussed and SRS Planned | 2025-12-09 | 2025-12-10 | Shivamani | others | 3-completed | 1.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Tech Stack Finalized and GIT initialization and repository setup | 2025-12-11 | 2025-12-13 | Shivamani | others | 3-completed | 2.5 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 4 | Project Initialization and Concepts and Brainstroming | 2025-12-14 | 2025-12-17 | Shivamani | others | 3-completed | 4.5 | 0.5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 5 | Libraries and Workflow and Basic Whisper Setup | 2025-12-18 | 2025-12-20 | Shivamani | others | 3-completed | 3 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 6 | Concepts of Different types Embedding and Tranformers | 2025-12-21 | 2025-12-24 | Shivamani | others | 3-completed | 3.5 | 0.5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 7 | Natural Language Processing and AI API's | 2025-12-25 | 2025-12-27 | Shivamani | others | 3-completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 8 | RAG Concepts & RAG Inplementation Overview | 2025-12-28 | 2025-12-31 | Shivamani | coding | 3-completed | 3.5 | 0.5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 9 | Make Application Orchestrator & Audio Processor | 2026-01-04 | 2026-01-06 | Shivamani | coding | 3-completed | 3 | 0.5 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 10 | Chat Normalizer & DB Manager and RAG engine | 2026-01-07 | 2026-01-08 | Shivamani | coding | 3-completed | 3 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | 11 | Auditor & Reporting | 2026-01-09 | 2026-01-11 | Shivamani | coding | 3-completed | 2.5 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 12 | Bugs Error fixing code upts policy update personal reporting code | 2026-01-12 | 2026-01-17 | Shivamani | System Test | 3-completed | 6 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 13 | Handling env variables and policy fiies | 2026-01-18 | 2026-01-19 | Shivamani | coding | 3-completed | 2 | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 14 | Theory and Implementation of Docker & DOCKER CONFIGURATION | 2026-01-20 | 2026-01-22 | Shivamani | coding | 3-completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 15 | DOCKER IMAGE AND CONTAINER | 2026-01-23 | 2026-01-24 | Shivamani | others | 3-completed | 3.5 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | 16 | Documentation and Implementation | 2026-01-25 | 2026-01-31 | Shivamani | others | 3-completed | 6 | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
sprint2 | Day 9 | Performance of the Diarizer | Found alternatives like Senko
sprint2 | Day 10 | Wheel issue | Download C++ Visual Studio and rollback python
sprint4 | Day 36 | Wheel system Dependency | Moved to Docker
sprint4 | Day 37 | Policy inefficent | Collected Data and made a proper file

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | sprint 1 | Dec 08 2025 | Dec 12 2025 | ALL | Basics of the project | Until the prerequisites gathered and tech Stack Finalized | Attended Classes Everyday | Gathered Resources and Finalized the plan of action on project
2 | sprint 2 | Dec 13 2025 | Dec 20 2025 | ALL | Maintaining code modularity | Writing unstructured codes | Diarization and Further setup | Use principles of HLD & LLD
3 | sprint 4 | Dec 20 2025 | Dec 27 2025 | ALL | Env variables and dependcies standards | using alternative packages | Setup Like Docker | Used Docker to resolve the issue